## About
Transmittals/Submittals: On the Input sheet, select the specification section and provide relevant information. Delete any descriptions that are not being submitted at this time or add descriptions as needed, Save Data, view, and print transmittals and their logs. Update on the Update sheet. Attachments: / Utilize the cloud! Share your files and copy and paste the link in the Attachment Link cell on the form. Select the cell and paste the URL of your attachment in the formula bar. File must be stored on a cloud-based file-sharing site like GoogleDrive and shareable. / When the forms are printed with the Microsoft Print to PDF, the link is the attachment. This is very useful when the updated submittal log is published, the links on the PDF document are the submittals. / Tip: When attaching a submittal for review, give the A/E 'can edit' rights so it can be marked up in place. When the review is complete, the A/E can download it for record. After review, stop sharing and change the link to anyone with a link 'can view'. This will make the submittal link available to anyone on the Submittal Log PDF document.

## Input
Specification Section	Description	Subcontractor:	Submit By:	DATE:	Attachments Link:			Log 9	Log 10	Log 11	Log 12	Date Returned:	Remaks:	Update 3		Refresh
Number	#1 Description1, #2 Description2, #3 Description3, #4 Description4, #5 Description5, #6 Description6, #7 Description7, #8 Description8, #9 Description9, #10 Description10	0	Submit By	2/20/2024	0
LETTER OF TRANSMITTAL
Company
		JOB:	Example Project

Business Street		DATE:	2/20/2024
Business City, Business State Business Postal Code
PHONE:	Business Phone	RE:	Specification Section		Number
FAX:	Business Fax		Description

TO:
Company
Business Street
Business City, Business State Business Postal Code

ATTN:	First Name Middle Name Last Name
Email:	E-mail Address
We are sending:

QTY	DATED	DESCRIPTION					#1 Description1, #2 Description2, #3 Description3, #4 Description4, #5 Description5, #6 Description6, #7 Description7, #8 Description8, #9 Description9, #10 Description10
		#1 Description1
		#2 Description2
		#3 Description3
		#4 Description4
		#5 Description5
		#6 Description6
		#7 Description7
		#8 Description8
		#9 Description9
		#10 Description10

These are transmitted for your review.

PLEASE NOTE THE FOLLOWING:

SIGNED:___
Subcontractor:
			Submit By:	Submit By
CC:			Date Returned:
		Attachments Link:
			Remaks:

## View_Print
33000- 33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , , - Company- 45298- 45342- https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link- - - - - -					Date Returned:	Remaks:	Update 3
	33000- 33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , , - Company- 45298- 45342- https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link- - - - - -					0	0	0
LETTER OF TRANSMITTAL					0	0	0	0	0	0	0	0	0	0
Company		0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		JOB:	Example Project				0	0	0	0	0	0	0	0	0	0
		0	0				0	0	0	0	0	0	0	0	0	0
Business Street		DATE:	2/20/2024		0	0	0	0	0	0	0	0	0	0	0	0
Business City, Business State Business Postal Code			0	0	0	0	0	0	0	0	0	0	0	0	0	0
PHONE:	Business Phone	RE:	Specification Section				0	0	0	0	0	0	0	0	0	0
FAX:	Business Fax	0	Concrete				0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
TO:	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Company			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Business Street			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Business City, Business State Business Postal Code			0	0	0	0	0	0	0	0	0	0	0	0	0	0
0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
ATTN:	First Name Middle Name Last Name			0	0	0	0	0	0	0	0	0	0	0	0	0
Email:	E-mail Address			0	0	0	0	0	0	0	0	0	0	0	0	0
We are sending:					0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
QTY	DATED	DESCRIPTION					33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , ,	0	0	0	0	0	0	0	0	0
1	1899-12-30	33000 -1.4.1 1. Manufacturer's Data					0	0	0	0	0	0	0	0	0	0
1	0	33000 - 1.4.2 2. Shop Drawings					0	0	0	0	0	0	0	0	0	0
1	0	33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials					0	0	0	0	0	0	0	0	0	0
0	0	0					0	0	0	0	0	0	0	0	0	0
0	0	0					0	0	0	0	0	0	0	0	0	0
0	0	0					0	0	0	0	0	0	0	0	0	0
0	0	0					0	0	0	0	0	0	0	0	0	0
0	0	0					0	0	0	0	0	0	0	0	0	0
0	0	0					0	0	0	0	0	0	0	0	0	0
0	0	0					0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
These are transmitted for your review.					0	0	0	0	0	0	0	0	0	0
				0	0	0	0	0	0	0	0	0	0
	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
PLEASE NOTE THE FOLLOWING:					0	0	0	0	0	0	0	0	0	0
kjvlk/ldfkj					0	0	0	0	0	0	0	0	0	0
				0	0	0	0	0	0	0	0	0	0
				0	0	0	0	0	0	0	0	0	0
				0	0	0	0	0	0	0	0	0	0
SIGNED:___	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Subcontractor:			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Company			Submit By:	1/7/2024	0	0	0	0	0	0	0	0	0	0	0	0
CC:	0	0	Date Returned:	0	0	0	0	0	0	0	0	0	0	0	0	0
0	0	Attachments Link:		https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link			0	0	0	0	0	0	0	0	0	0
0	0	0	Remaks:	0			0	0	0	0	0	0	0	0	0	0
0	0	0	0				0	0	0	0	0	0	0	0	0	0
0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

## Log
Example Project		Company
Submittal Log
Date	2/20/2024

Specification Section	Description	Subcontractor:	Submit By:	DATE:	Attachments Link:	0	0	Log 9	Log 10	Log 11	Log 12	Date Returned:	Remaks:	Update 3
33000	33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , ,	Company	1/7/2024	2/20/2024	https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link	0	0	0	0	0	0	0	0	0
0	0	0	12/30/1899	12/30/1899	0	0	0	0	0	0	0	0	0	0
0	0	0	12/30/1899	12/30/1899	0	0	0	0	0	0	0	0	0	0
0	0	0	12/30/1899	12/30/1899	0	0	0	0	0	0	0	0	0	0
0	0	0	12/30/1899	12/30/1899	0	0	0	0	0	0	0	0	0	0

## Update
	Date Returned:	Remaks:	Update 3	Specification Section	Description	Subcontractor:	Submit By:	DATE:	Attachments Link:	0	0	Log 9	Log 10	Log 11	Log 12
33000- 33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , , - Company- 45298- 45342- https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link- - - - - -				33000	33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , ,	45298	45298	45342	https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link	0	0	0	0	0	0
0				0	0	0	0	0	0	0	0	0	0	0	0
0				0	0	0	0	0	0	0	0	0	0	0	0
0				0	0	0	0	0	0	0	0	0	0	0	0
0	2/13/24	reviewed as noted		0	0	0	0	0	0	0	0	0	0	0	0

## SubmittalSchedule
Example Project

This is sample data enter or paste your project specific submittal requirements.

Number	Description	Submit By	#1	Description1	#2	Description2	#3	Description3	#4	Description4	#5	Description5	#6	Description6	#7	Description7	#8	Description8	#9	Description9	#10	Description10	#1 Description1	#2 Description2	#3 Description3	#4 Description4	#5 Description5	#6 Description6	#7 Description7	#8 Description8	#9 Description9	#10 Description10
13216	Construction Schedule	1/4/2024	01 3216 - 1.6.A	INITIAL SCHEDULE					01 3216 - 1.6.A INITIAL SCHEDULE
24119.01	Minor Demolition for Remodeling	1/5/2024	24119.01 - 1.3.A.1	1. Provide a detailed sequence of demolition and removal work to ensure uninterrupted progress of Owner's on-site operations.	24119.01 - 1.3.A.2	2. Include in schedule coordination for shut-off, capping of utilities, and disconnection of equipment as required.	24119.01 - 1.3.B	Submit in accordance with Section 01 7700: Record drawings.					24119.01 - 1.3.A.1 1. Provide a detailed sequence of demolition and removal work to ensure uninterrupted progress of Owner's on-site operations.	24119.01 - 1.3.A.2 2. Include in schedule coordination for shut-off, capping of utilities, and disconnection of equipment as required.	24119.01 - 1.3.B Submit in accordance with Section 01 7700: Record drawings.
15000	Temporary Facilities and Controls	1/5/2024	01 5000 - 1.3	1. Site Logistics Plan					01 5000 - 1.3 1. Site Logistics Plan
16000	Product Requirements	1/5/2024	01 6000 - 1.5.1	1. Request for allocation of storage space.	01 6000 - 1.5.2	2. List of materials and equipment to be stored.	01 6000 - 1.5.3	3. Proposed location for storage	01 6000 - 1.5.4	4. Special storage requirements	01 6000 - 1.5.5	5. Schedule of anticipated storage dates.					01 6000 - 1.5.1 1. Request for allocation of storage space.	01 6000 - 1.5.2 2. List of materials and equipment to be stored.	01 6000 - 1.5.3 3. Proposed location for storage	01 6000 - 1.5.4 4. Special storage requirements	01 6000 - 1.5.5 5. Schedule of anticipated storage dates.
33000	Concrete	1/7/2024	33000 -1.4.1	1. Manufacturer's Data	33000 - 1.4.2	2. Shop Drawings	33000 - 1.4.3	3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials					33000 -1.4.1 1. Manufacturer's Data	33000 - 1.4.2 2. Shop Drawings	33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials
42000	Unit Masonry	2/1/2024	42000 - 1.4.1	1. Product data	42000 - 1.4.2	2. Samples:	42000 - 1.4.3	3. Certificates	42000 - 1.4.4	4. Cold-Weather Procedures	42000 - 1.4.5	5. Testing Agency qualifications					42000 - 1.4.1 1. Product data	42000 - 1.4.2 2. Samples:	42000 - 1.4.3 3. Certificates	42000 - 1.4.4 4. Cold-Weather Procedures	42000 - 1.4.5 5. Testing Agency qualifications
31 2000	Earthwork	2/1/2024	31 200 - 1.6.1	1. Test Reports	31 200 - 1.6.2	2. Filter fabric	31 200 - 1.6.3	3. Test Report on Fill Material	31 200 - 1.6.4	4. Product Certification	31 200 - 1.6.5	5. Topsoil Analysis Report	31 200 - 1.6.6	6. Testing Agency qualifications					31 200 - 1.6.1 1. Test Reports	31 200 - 1.6.2 2. Filter fabric	31 200 - 1.6.3 3. Test Report on Fill Material	31 200 - 1.6.4 4. Product Certification	31 200 - 1.6.5 5. Topsoil Analysis Report	31 200 - 1.6.6 6. Testing Agency qualifications
17329	Cutting and Patching	2/6/2024	01 7329 - 1.3	A. Submit written request in advance of cutting or alteration					01 7329 - 1.3 A. Submit written request in advance of cutting or alteration
260500	Common Work Results for Electrical	3/1/2024	260500 -1.4.A	A. Product Data:					260500 -1.4.A A. Product Data:
260519	Low-Voltage Electrical Power Conductors and Cables	3/1/2024	260519 - 1.4.A	A. Product Data:	260519 - 1.4.B	B. Qualification Data:	260519 - 1.4.C	C. Field quality-control test reports					260519 - 1.4.A A. Product Data:	260519 - 1.4.B B. Qualification Data:	260519 - 1.4.C C. Field quality-control test reports
260526	Grounding and Bonding for Electrical Systems	3/1/2024	260526 - 1.3.A	A. Product Data	260526 - 1.3.B	B. Other Informational Submittals	260526 - 1.3.C	C. Qualification Data	260526 - 1.3.D	D. Field quality-control test reports					260526 - 1.3.A A. Product Data	260526 - 1.3.B B. Other Informational Submittals	260526 - 1.3.C C. Qualification Data	260526 - 1.3.D D. Field quality-control test reports
260529	Hangers and Supports for Electrical Systems	3/1/2024	260529 - 1.4.A	A. Product Data:	260529 - 1.4.B	B. Shop Drawings					260529 - 1.4.A A. Product Data:	260529 - 1.4.B B. Shop Drawings
260533	Raceways and Boxes for Electrical Systems	3/1/2024	260533 - 1.4.A	A. Product Data:	260533 - 1.4.B	B. Shop Drawings					260533 - 1.4.A A. Product Data:	260533 - 1.4.B B. Shop Drawings
31 3116	Termite Control	3/1/2024	31 3116 - 1.5.A.1	1. Manufacturer's Literature and Product Data	31 3116 - 1.5.A.2	2. Service Agreement	31 3116 - 1.5.B.1	1. Soil Treatment Application Reports					31 3116 - 1.5.A.1 1. Manufacturer's Literature and Product Data	31 3116 - 1.5.A.2 2. Service Agreement	31 3116 - 1.5.B.1 1. Soil Treatment Application Reports
44200	Stone Cladding	3/15/2024	44200 - 1.4.1	1. Indicate on shop drawings; layout; pertinent dimensions; anchorages; reinforcement; head, jamb, and sill opening details; and control and expansion jointing methods.	44200 - 1.4.2	2. Provide product data on stone units, mortar products, reinforcements, and other pertinent items.	44200 - 1.4.3	3. Samples: Submit two samples 12" x 12" in size illustrating color range and texture, markings, surface finish, and other features.	44200 - 1.4.4	4. Manufacturer's installation instructions	44200 - 1.4.5	5. Field erection or setting drawings. Indicate on setting drawings, panel identifying marks and locations.					44200 - 1.4.1 1. Indicate on shop drawings; layout; pertinent dimensions; anchorages; reinforcement; head, jamb, and sill opening details; and control and expansion jointing methods.	44200 - 1.4.2 2. Provide product data on stone units, mortar products, reinforcements, and other pertinent items.	44200 - 1.4.3 3. Samples: Submit two samples 12" x 12" in size illustrating color range and texture, markings, surface finish, and other features.	44200 - 1.4.4 4. Manufacturer's installation instructions	44200 - 1.4.5 5. Field erection or setting drawings. Indicate on setting drawings, panel identifying marks and locations.
47200	Cast Stone Masonry	3/15/2024	47200 - 1.4.A.1	1 . Test results of cast stone previously made by the manufacturer	47200 - 1.4A.2	2. Product data	47200 -1.4A-3	3. Samples	47200 - 1.4A-4	4. Shop drawings	47200 - 1.4.B	1. Project Record Documents					47200 - 1.4.A.1 1 . Test results of cast stone previously made by the manufacturer	47200 - 1.4A.2 2. Product data	47200 -1.4A-3 3. Samples	47200 - 1.4A-4 4. Shop drawings	47200 - 1.4.B 1. Project Record Documents
61000	Rough Carpentry	3/15/2024	61000 -1.4.1	1. Submit technical data on wood treatment materials and application instructions					61000 -1.4.1 1. Submit technical data on wood treatment materials and application instructions
81100	Metal Doors and Frames	3/15/2024	81100 -1.4.A.1	1. Manufacturer's Data	81100 - 1.4.A.2	2. Shop Drawings	81100 - 1.4.A.3	3. Label Construction					81100 -1.4.A.1 1. Manufacturer's Data	81100 - 1.4.A.2 2. Shop Drawings	81100 - 1.4.A.3 3. Label Construction
51200	Structural Steel	4/1/2024	51200 - 1.6	1. Shop Drawings, 2. Statement of Qualifications					51200 - 1.6 1. Shop Drawings, 2. Statement of Qualifications
52100	Steel Joists	4/1/2024	52100 - 1.4.1	1. Shop Drawings	52100 - 1.4.2	2. Welders' Certificates	52100 - 1.4.3	3. Manufacturer's Data					52100 - 1.4.1 1. Shop Drawings	52100 - 1.4.2 2. Welders' Certificates	52100 - 1.4.3 3. Manufacturer's Data
53100	Steel Deck	4/1/2024	53100 - 1.4.1	1. Product Data:	53100 - 1.4.2	2. Shop Drawings	53100 - 1.4.3	3. Calculations	53100 - 1.4.4	4. Welder Qualifications					53100 - 1.4.1 1. Product Data:	53100 - 1.4.2 2. Shop Drawings	53100 - 1.4.3 3. Calculations	53100 - 1.4.4 4. Welder Qualifications
55000	Metal Fabrications	4/1/2024	55000 -1.6.1	1. Shop Drawings	55000 - 1.6.2	2. Submit fabricator's qualification documentation	55000 - 1.6.3	3. Product Data	55000 - 1.6.4	4. Samples of products and materials when requested	55000 - 1.6.5	5. Submittal List:					55000 -1.6.1 1. Shop Drawings	55000 - 1.6.2 2. Submit fabricator's qualification documentation	55000 - 1.6.3 3. Product Data	55000 - 1.6.4 4. Samples of products and materials when requested	55000 - 1.6.5 5. Submittal List:
92100	Gypsum Board Assemblies	4/1/2024	92100 - 1.4.A.1	1. Manufacturer's Data					92100 - 1.4.A.1 1. Manufacturer's Data
213113	Electric-Drive, Centrifugal Fire Pumps	4/1/2024	213113 - 1.4.A	A. Product Data	213113 - 14.B	B. Shop Drawings	213113 - 14.C	C. Seismic Qualification Certificates	213313 - 14.D	D. Product Certificates	213313 - 14.E	E. Source quality-control reports.	213313 - 14.F	F. Field quality-control reports	213313 - 14.G	G. Operation and Maintenance Data					213113 - 1.4.A A. Product Data	213113 - 14.B B. Shop Drawings	213113 - 14.C C. Seismic Qualification Certificates	213313 - 14.D D. Product Certificates	213313 - 14.E E. Source quality-control reports.	213313 - 14.F F. Field quality-control reports	213313 - 14.G G. Operation and Maintenance Data
220500	Common Work Results for Plumbing	4/1/2024	220500 - 1.4.A	A. Product Data					220500 - 1.4.A A. Product Data
220519	Meters and Gages for Plumbing Piping	4/1/2024	220519 - 1.4.A	A. Product Data					220519 - 1.4.A A. Product Data
220523	General-Duty Valves for Plumbing Piping	4/1/2024	220523 - 1.4.A	A. Product Data					220523 - 1.4.A A. Product Data
220529	Hangers and Supports for Plumbing Piping and Equipment	4/1/2024	220529 - 1.5.A	A. Product Data					220529 - 1.5.A A. Product Data
220553	Identification for Plumbing Piping and Equipment	4/1/2024	220553 - 1.3.A	A. Product Data	220553 - 1.3.B	B. Samples	220553 - 1.3.C	C. Equipment Label Schedule	220553 - 1.3.D	D. Valve numbering scheme	220553 - 1.3.E	E. Valve Schedules					220553 - 1.3.A A. Product Data	220553 - 1.3.B B. Samples	220553 - 1.3.C C. Equipment Label Schedule	220553 - 1.3.D D. Valve numbering scheme	220553 - 1.3.E E. Valve Schedules
220700	Plumbing Insulation	4/1/2024	220700 -1.3.A	A. Product Data					220700 -1.3.A A. Product Data
221013	Facility Natural-Gas Piping	4/1/2024	221013 - 1.5.A	A. Product Data	221013 - 1.5.B	B. Operation and Maintenance Data					221013 - 1.5.A A. Product Data	221013 - 1.5.B B. Operation and Maintenance Data
221116	Domestic Water Piping	4/1/2024	221116 - 1.4.A	A. Product Data	221116 - 1.4.B	B. Water Samples	221116 - 1.4.C	C. Field quality-control test reports					221116 - 1.4.A A. Product Data	221116 - 1.4.B B. Water Samples	221116 - 1.4.C C. Field quality-control test reports
221119	Domestic Water Piping Specialties	4/1/2024	221119 -1.4.A	A. Product Data	221119 - 1.4.B	B. Field quality-control test reports	221119 - 1.4.C	C. Operation and Maintenance Data					221119 -1.4.A A. Product Data	221119 - 1.4.B B. Field quality-control test reports	221119 - 1.4.C C. Operation and Maintenance Data
221123	Domestic Water Pumps	4/1/2024	221123 - 1.4.A	A. Product Data					221123 - 1.4.A A. Product Data
221316	Sanitary Waste and Vent Piping	4/1/2024	221316 - 1.4.A	A. Product Data					221316 - 1.4.A A. Product Data
221319	Sanitary Waste Piping Specialties	4/1/2024	221319 - 1.3.A	A. Product Data	221319 -1.3.B.	B. Operation and Maintenance Data					221319 - 1.3.A A. Product Data	221319 -1.3.B. B. Operation and Maintenance Data
221413	Facility Storm Drainage Piping	4/1/2024	221413 - 1.3.A	A. Roof drains.					221413 - 1.3.A A. Roof drains.
221429	Sump Pumps	4/1/2024	221429 - 1.3.A	A. Product Data	221429 - 1.3.B	B. Wiring Diagrams	221429 - 1.3.C.	C. Operation and maintenance data					221429 - 1.3.A A. Product Data	221429 - 1.3.B B. Wiring Diagrams	221429 - 1.3.C. C. Operation and maintenance data
223400	Fuel-Fired Domestic Water Heaters	4/1/2024	223400 - 1.3.A	A. Product Data	223400 - 1.3.B	B. Shop Drawings	223400 - 1.3.C	C. Product Certificates:	223400 - 1.3.D	D. Source quality-control test reports	223400 - 1.3.E	E. Field quality-control test reports	223400 - 1.3.F	F. Operation and Maintenance Data	223400 - 1.3.G	G. Warranty					223400 - 1.3.A A. Product Data	223400 - 1.3.B B. Shop Drawings	223400 - 1.3.C C. Product Certificates:	223400 - 1.3.D D. Source quality-control test reports	223400 - 1.3.E E. Field quality-control test reports	223400 - 1.3.F F. Operation and Maintenance Data	223400 - 1.3.G G. Warranty
224000	Plumbing Fixtures	4/1/2024	224000 - 1.4.A.	A. Product Data:	224000 - 1.A.B	B. Shop Drawings	224000 - 1.A.C	C. Operation and Maintenance Data	224000 - 1.A.D	D. Warranty					224000 - 1.4.A. A. Product Data:	224000 - 1.A.B B. Shop Drawings	224000 - 1.A.C C. Operation and Maintenance Data	224000 - 1.A.D D. Warranty
21 0500	Common Work Results for Fire Suppression	4/1/2024	21 0500 - 1.4.A	Product Data	21 0500 - 1.4.B	Welding certificates					21 0500 - 1.4.A Product Data	21 0500 - 1.4.B Welding certificates
21 1000	Water-Based Fire-Suppression Systems	4/1/2024	21 1000 -1.5.A	A. Product Data	21 1000 -1.5.B	B. Shop Drawings	21 1000 -1.5.C	C. Fire-hydrant flow test report	21 1000 -1.5.D	D. Approved Sprinkler Piping Drawings	21 1000 -1.5-E	E. Field Test Reports and Certificates	21 1000 -1.5.F	F. Welding certificates	21 1000 - 1.5.G	G. Field quality-control test reports	21 1000 - 1.5.H	H. Operation and Maintenance Data					21 1000 -1.5.A A. Product Data	21 1000 -1.5.B B. Shop Drawings	21 1000 -1.5.C C. Fire-hydrant flow test report	21 1000 -1.5.D D. Approved Sprinkler Piping Drawings	21 1000 -1.5-E E. Field Test Reports and Certificates	21 1000 -1.5.F F. Welding certificates	21 1000 - 1.5.G G. Field quality-control test reports	21 1000 - 1.5.H H. Operation and Maintenance Data
72100	Building Insulation	4/15/2024	72100 - 1.4.1	1. Manufacturer's Data					72100 - 1.4.1 1. Manufacturer's Data
142400	Hydraulic Elevators	4/15/2024	142400 - 1.4.A.1	1. Product Data	142400 - 1.4.A.2	2. Shop Drawings	142400 - 1.4.A.3	3. Samples	142400 - 1.4.A.4	4. Manufacturer Certificates	142400 - 1.4.A.5	5. Submit "Continuing Maintenance Service" proposal	142400 - 1.4.B.1	1. O&M Data	142400 - 1.4.B.2	2. Control Wiring Diagrams					142400 - 1.4.A.1 1. Product Data	142400 - 1.4.A.2 2. Shop Drawings	142400 - 1.4.A.3 3. Samples	142400 - 1.4.A.4 4. Manufacturer Certificates	142400 - 1.4.A.5 5. Submit "Continuing Maintenance Service" proposal	142400 - 1.4.B.1 1. O&M Data	142400 - 1.4.B.2 2. Control Wiring Diagrams
260923	Lighting Control Devices	4/15/2024	260923 - 1.4.A	A. Product Data:	260923 - 1.4.B	B. Shop Drawings	260923 - 1.4.C	C. Field quality-control test reports.	260923 - 1.4.D	D. Operation and Maintenance Data					260923 - 1.4.A A. Product Data:	260923 - 1.4.B B. Shop Drawings	260923 - 1.4.C C. Field quality-control test reports.	260923 - 1.4.D D. Operation and Maintenance Data
262200	Low-Voltage Transformer	4/15/2024	262200 - 1.3.A	A. Product Data:	262200 - 1.3.B	B. Shop Drawings	262200 - 1.3.C	C. Qualification Data	262200 - 1.3.D	D. Source quality-control test reports	262200 - 1.3.E	E. Field quality-control test reports	262200 - 1.3.F	F. Operation and Maintenance Data					262200 - 1.3.A A. Product Data:	262200 - 1.3.B B. Shop Drawings	262200 - 1.3.C C. Qualification Data	262200 - 1.3.D D. Source quality-control test reports	262200 - 1.3.E E. Field quality-control test reports	262200 - 1.3.F F. Operation and Maintenance Data
262413	Switchboards	4/15/2024	262413 - 1.4.A	A. Product Data:	262413 - 1.4.B	B. Shop Drawings	262413 - 1.4.C	C. Operation and Maintenance Data:					262413 - 1.4.A A. Product Data:	262413 - 1.4.B B. Shop Drawings	262413 - 1.4.C C. Operation and Maintenance Data:
262416	Panelsboards	4/15/2024	262416 - 1.4.A	A. Product Data:	262416 - 1.4.B	B. Shop Drawings	262416 - 1.4.C	C. Field quality-control test reports	262416 - 1.4.D	D. Panelboard Schedules:	262416 - 1.4.E	E. Operation ;and Maintenance Data					262416 - 1.4.A A. Product Data:	262416 - 1.4.B B. Shop Drawings	262416 - 1.4.C C. Field quality-control test reports	262416 - 1.4.D D. Panelboard Schedules:	262416 - 1.4.E E. Operation ;and Maintenance Data
262713	Electricity Metering	4/15/2024	262713 - 1.3.A	A. Product Data:	262713 - 1.3.B	B. Shop Drawings					262713 - 1.3.A A. Product Data:	262713 - 1.3.B B. Shop Drawings
262726	Wiring Devices	4/15/2024	262726 - 1.4.A	A. Product Data:	262726 - 1.4.B	B. Shop Drawings	262726 -1.4.C	C. Field quality-control test reports	262726 - 1.4.D	D. Operation and Maintenance Data:					262726 - 1.4.A A. Product Data:	262726 - 1.4.B B. Shop Drawings	262726 -1.4.C C. Field quality-control test reports	262726 - 1.4.D D. Operation and Maintenance Data:
262816	Enclosed Switches and Circuit Breakers	4/15/2024	262816 - 1.4.A	A. Product Data:	262816 - 1.4.B	B. Shop Drawings	262816 - 1.4.C	C. Field quality-control test reports	262816 - 1.4.D	D. Manufacturer's field service report					262816 - 1.4.A A. Product Data:	262816 - 1.4.B B. Shop Drawings	262816 - 1.4.C C. Field quality-control test reports	262816 - 1.4.D D. Manufacturer's field service report
262913	Enclosed Controllers	4/15/2024	262913 - 1.3.A	A. Product Data:	262913 - 1.3.B	B. Shop Drawings	262913 - 1.3.C	C. Coordination Drawings	262913 - 1.3.D	D. Field quality-control test reports	262913 - 1.3.E	E. Operation and Maintenance Data	262913 - 1.3.F	F. Load-Current and Overload-Relay Heater List	262913 - 1.3.G	G. Load-Current and List of Settings of Adjustable Overload Relays					262913 - 1.3.A A. Product Data:	262913 - 1.3.B B. Shop Drawings	262913 - 1.3.C C. Coordination Drawings	262913 - 1.3.D D. Field quality-control test reports	262913 - 1.3.E E. Operation and Maintenance Data	262913 - 1.3.F F. Load-Current and Overload-Relay Heater List	262913 - 1.3.G G. Load-Current and List of Settings of Adjustable Overload Relays
265100	Interior Lighting	4/15/2024	265100 - 1.4.A	A. Product Data:	265100 - 1.4.B	B. Field quality-control test reports.	265100 - 1.4.C	C. Operation and Maintenance Data	265100 - 1.4.D	D. Warranties					265100 - 1.4.A A. Product Data:	265100 - 1.4.B B. Field quality-control test reports.	265100 - 1.4.C C. Operation and Maintenance Data	265100 - 1.4.D D. Warranties
265561	Theatrical Lighting	4/15/2024	652261 - 1.6	If required by the Architect or Engineer Samples	652261 - 1.7	Shop Drawings	652261 - 1.8	Warranties					652261 - 1.6 If required by the Architect or Engineer Samples	652261 - 1.7 Shop Drawings	652261 - 1.8 Warranties
265600	Exterior Lighting	4/15/2024	265600 - 1.4.A	A. Product Data:	265600 - 1.4.B	B. Shop Drawings	265600 - 1.4.C	C. Operation and Maintenance Data	265600 - 1.4.D	D. Warranty					265600 - 1.4.A A. Product Data:	265600 - 1.4.B B. Shop Drawings	265600 - 1.4.C C. Operation and Maintenance Data	265600 - 1.4.D D. Warranty
283111	Digital, Addressable Fire-Alarm System	4/15/2024	283111 - 1.5.B	B. Product Data	283111 - 1.5.C	C. Shop Drawings	283111 - 1.5.D	D. Qualification Data:	283111 - 1.5.E	E. Field quality-control reports	283111 - 1.5.F	F. Operation and Maintenance Data	283111 - 1.5.G	G. Software and Firmware Operational Documentation					283111 - 1.5.B B. Product Data	283111 - 1.5.C C. Shop Drawings	283111 - 1.5.D D. Qualification Data:	283111 - 1.5.E E. Field quality-control reports	283111 - 1.5.F F. Operation and Maintenance Data	283111 - 1.5.G G. Software and Firmware Operational Documentation
72400	Direct Applied Exterior Finish System (DEFS)	5/1/2024	72400 - 1.4.B	B. Product Data	72400 -1.4.C	C. Shop Drawings	72400 - 1.4.D	D. Sample					72400 - 1.4.B B. Product Data	72400 -1.4.C C. Shop Drawings	72400 - 1.4.D D. Sample
104116	Security Equipment	5/1/2024	104116 - 1.3.A.1	1. Manufacturer's Data	104116 - 1.3.A.2	2. Shop Drawings					104116 - 1.3.A.1 1. Manufacturer's Data	104116 - 1.3.A.2 2. Shop Drawings
329000	Planting	5/1/2024	329000 - 1.4.A.1	1. Product certificates	329000 - 1.4.A.2	2. Certification of grass seed	329000 - 1.4.A.3	3. Qualification data	329000 - 1.4.A.4	4. Material test reports	329000 - 1.4.A.5	5. Planting schedule					329000 - 1.4.A.1 1. Product certificates	329000 - 1.4.A.2 2. Certification of grass seed	329000 - 1.4.A.3 3. Qualification data	329000 - 1.4.A.4 4. Material test reports	329000 - 1.4.A.5 5. Planting schedule
75423	Thermoplastic Polyolefin (TPO) Membrane Roofing	5/15/2024	75423 - 1.5.B.1	1. Submit shop drawings and product data	75423 - 1.5.B.2	2. Installer certificate	75423 - 1.5.C.1	1. Provide warranty certificates					75423 - 1.5.B.1 1. Submit shop drawings and product data	75423 - 1.5.B.2 2. Installer certificate	75423 - 1.5.C.1 1. Provide warranty certificates
76200	Sheet Metal Flashing & Trim	5/15/2024	76200 -1.5.A.1	1. Submit shop drawings and product data	76200 - 1.5.A.2	2. Qualification data for firms and persons specified					76200 -1.5.A.1 1. Submit shop drawings and product data	76200 - 1.5.A.2 2. Qualification data for firms and persons specified
77000	Roof Specialties & Accessories	5/15/2024	77000 - 1.4.A.1	1. Submit shop drawings, manufacturer's installation instructions, and product data.					77000 - 1.4.A.1 1. Submit shop drawings, manufacturer's installation instructions, and product data.
230500	Common Work Results for HVAC	5/15/2024	230500 - 1.4.A	A. Product Data:	230500 - 1.4.B	B. Welding certificates					230500 - 1.4.A A. Product Data:	230500 - 1.4.B B. Welding certificates
230519	Meters and Gages for HVAC Piping	5/15/2024	230519 -1.3.A	A. Product Data	230519 - 1.3.B	B. Wiring Diagrams	230519 -1.3.C	C. Product Certificates					230519 -1.3.A A. Product Data	230519 - 1.3.B B. Wiring Diagrams	230519 -1.3.C C. Product Certificates
230523	General-Duty Valves for HVAC Piping	5/15/2024	230523 -1.4.A	A. Product Data					230523 -1.4.A A. Product Data
230529	Hangers and Supports for HVAC Piping and Equipment	5/15/2024	230529 - 1.5.A	A. Product Data	230529 - 1.5.B	B. Shop Drawings	2330529 - 1.5.C	C. Welding certificates					230529 - 1.5.A A. Product Data	230529 - 1.5.B B. Shop Drawings	2330529 - 1.5.C C. Welding certificates
230548	Vibration and Seismic Controls for HVAC Piping and Equipment	5/15/2024	230548 - 1.4.A	A. Product Data	230548 - 1.4.B	B. Delegated-Design Submittal	230548 - 1.4.C	C. Riser Supports	230548 -1.4.D	D. Field quality-control test reports					230548 - 1.4.A A. Product Data	230548 - 1.4.B B. Delegated-Design Submittal	230548 - 1.4.C C. Riser Supports	230548 -1.4.D D. Field quality-control test reports
230553	Identification for HVAC Piping and Equipment	5/15/2024	230553 - 1.3.A	A. Product Data	230553 - 1.3.B	B. Samples	230553 - 1.3.C	C. Equipment Label Schedule	230553 - 1.3.D	D. Valve numbering scheme	230553 - 1.3.E	E. Valve Schedules					230553 - 1.3.A A. Product Data	230553 - 1.3.B B. Samples	230553 - 1.3.C C. Equipment Label Schedule	230553 - 1.3.D D. Valve numbering scheme	230553 - 1.3.E E. Valve Schedules
230593	Testing, Adjusting and Balancing for HVAC	5/15/2024	230593 - 1.4.A	A. Qualification Data:	230593 - 1.4.B	B. Certified TAB reports	230593 -1.4.C.	C. Instrument calibration reports					230593 - 1.4.A A. Qualification Data:	230593 - 1.4.B B. Certified TAB reports	230593 -1.4.C. C. Instrument calibration reports
230700	HVAC Insulation	5/15/2024	230700 - 1.3.A	A. Product Data					230700 - 1.3.A A. Product Data
230900	HVAC Instrumentation and Controls	5/15/2024	230900 - 1.5.A	A. Product Data	230900 - 1.5.B	B. Shop Drawings	230900 - 1.5.C	C. Data Communications Protocol Certificates ASHRAE 135	230900 - 1.5.D	D. Data Communications Protocol Certificates LonWorks	230900 - 1.5.E	E. Samples for Initial Selection	230900 - 1.5.F	F. Samples for Verification	230900 - 1.5.G	G. Software and Firmware Operational Documentation	230900 - 1.5.H	H. Software Upgrade Kit	230900 - 1.5.I	I. Qualification Data	230900 - 1.5.J	J. Field quality-control test reports	230900 - 1.5.A A. Product Data	230900 - 1.5.B B. Shop Drawings	230900 - 1.5.C C. Data Communications Protocol Certificates ASHRAE 135	230900 - 1.5.D D. Data Communications Protocol Certificates LonWorks	230900 - 1.5.E E. Samples for Initial Selection	230900 - 1.5.F F. Samples for Verification	230900 - 1.5.G G. Software and Firmware Operational Documentation	230900 - 1.5.H H. Software Upgrade Kit	230900 - 1.5.I I. Qualification Data	230900 - 1.5.J J. Field quality-control test reports
232113	Hydronic Piping	5/15/2024	232113 - 1.3.A	A. Product Data	232113 - 1.3.B	B. Welding certificates	232113 - 13.C	C. Qualification Data	232113 - 13.D	D. Field quality-control test reports					232113 - 1.3.A A. Product Data	232113 - 1.3.B B. Welding certificates	232113 - 13.C C. Qualification Data	232113 - 13.D D. Field quality-control test reports
232123	Hydronic Pumps	5/15/2024	232123 -1.4.A	A. Product Data	232123 -1.4.B	B. Shop Drawings	232123 -1.4.C	C. Operation and Maintenance Data					232123 -1.4.A A. Product Data	232123 -1.4.B B. Shop Drawings	232123 -1.4.C C. Operation and Maintenance Data
232500	HVAC Water Treatment	5/15/2024	232500 - 1.5.A	A. Product Data	232500 - 1.5.B	B. Shop Drawings	232500 - 1.5.C	C. Field quality-control test reports	232500 - 1.5.D	D. Other Informational Submittals					232500 - 1.5.A A. Product Data	232500 - 1.5.B B. Shop Drawings	232500 - 1.5.C C. Field quality-control test reports	232500 - 1.5.D D. Other Informational Submittals
233113	Metal Ducts	5/15/2024	233133 - 1.4.A	A. Product Data	233133 - 1.4.B	B. Shop Drawings					233133 - 1.4.A A. Product Data	233133 - 1.4.B B. Shop Drawings
233300	Air Duct Accessories	5/15/2024	233300 - 1.3.A	A. Product Data	233300 - 1.3.B	B. Shop Drawings	233300 - 1.3.C	C. Coordination Drawings	233300 - 1.3.D	D. Operation and Maintenance Data					233300 - 1.3.A A. Product Data	233300 - 1.3.B B. Shop Drawings	233300 - 1.3.C C. Coordination Drawings	233300 - 1.3.D D. Operation and Maintenance Data
233423	HVAC Power Ventilators	5/15/2024	233423 - 1.4.A	A. Product Data	233423 - 1.4.B	B. Shop Drawings	233423 - 1.4.C	C. Coordination Drawings	233423 - 1.4.D	D. Field quality-control test reports	233423 - 1.4.E	E. Operation and Maintenance Data					233423 - 1.4.A A. Product Data	233423 - 1.4.B B. Shop Drawings	233423 - 1.4.C C. Coordination Drawings	233423 - 1.4.D D. Field quality-control test reports	233423 - 1.4.E E. Operation and Maintenance Data
233713	Diffusers, Registers, and Grilles	5/15/2024	233713 - 1.3.A	A. Product Data	233713 - 1.3.B	B. Samples for Initial Selection	233713 - 1.3.C	C. Samples for Verification	233713 - 1.3.D	D. Coordination Drawings	233713 - 1.3.E	E. Source quality-control reports					233713 - 1.3.A A. Product Data	233713 - 1.3.B B. Samples for Initial Selection	233713 - 1.3.C C. Samples for Verification	233713 - 1.3.D D. Coordination Drawings	233713 - 1.3.E E. Source quality-control reports
233723	HVAC Gravity Ventilators	5/15/2024	233723 - 1.4.A	A. Product Data	233723 - 1.4.B	B. Shop Drawings					233723 - 1.4.A A. Product Data	233723 - 1.4.B B. Shop Drawings
235100	Breechings, Chimneys, and Stacks	5/15/2024	235100 - 1.3.A	A. Product Data	235100 - 1.3.B	B. Shop Drawings	235100 - 13.C	C. Warranty					235100 - 1.3.A A. Product Data	235100 - 1.3.B B. Shop Drawings	235100 - 13.C C. Warranty
235216	Condensing Biolers	5/15/2024	235216 - 1.3.A	A. Product Data	235216 - 1.3.B	B. Shop Drawings	235216 - 1.3.C	C. Manufacturer Seismic Qualification Certification	235216 - 1.3.D	D. Source quality-control test reports	235216 - 1.3.E	E. Field quality-control test reports	235216 - 1.3.F	F. Operation and Maintenance Data	235216 - 1.3.G	G. Warranty	235216 - 1.3.AH	H. Other Informational Submittals					235216 - 1.3.A A. Product Data	235216 - 1.3.B B. Shop Drawings	235216 - 1.3.C C. Manufacturer Seismic Qualification Certification	235216 - 1.3.D D. Source quality-control test reports	235216 - 1.3.E E. Field quality-control test reports	235216 - 1.3.F F. Operation and Maintenance Data	235216 - 1.3.G G. Warranty	235216 - 1.3.AH H. Other Informational Submittals
237433	Packaged, Outdoor, Heating and Cooling Makeup Air-Conditioners	5/15/2024	237433 - 1.3.A	A. Product Data	237433 - 1.3.B	B. Shop Drawings	237433- 1.3.C	C. Coordination Drawings	237433 -1.3.D	D. Startup service reports	237433 - 1.3.E	E. Operation and Maintenance Data	237433 - 1.3.F	F. Warranty					237433 - 1.3.A A. Product Data	237433 - 1.3.B B. Shop Drawings	237433- 1.3.C C. Coordination Drawings	237433 -1.3.D D. Startup service reports	237433 - 1.3.E E. Operation and Maintenance Data	237433 - 1.3.F F. Warranty
238146	Water-Source Unitary Heat Pumps	5/15/2024	238146 - 1.3.A	A. Product Data	238146 - 1.3.B	B. Shop Drawings	238146 - 1.3.C	C. Coordination Drawings	238146 - 1.3.D	D. Samples for Initial Selection	238146 - 1.3.E	E. Samples for Verification	238146 - 1.3.F	F. Product Certificates	238146 - 1.3.G	G. Field quality-control test reports	238146 - 1.3.H	H. Operation and Maintenance Data	238146 - 1.3.I	I. Warranty			238146 - 1.3.A A. Product Data	238146 - 1.3.B B. Shop Drawings	238146 - 1.3.C C. Coordination Drawings	238146 - 1.3.D D. Samples for Initial Selection	238146 - 1.3.E E. Samples for Verification	238146 - 1.3.F F. Product Certificates	238146 - 1.3.G G. Field quality-control test reports	238146 - 1.3.H H. Operation and Maintenance Data	238146 - 1.3.I I. Warranty
238223	Unit Ventilators	5/15/2024	238223 -1.4.A	A. Product Data	238223 - 1.4.B	B. Shop Drawings	238223 - 1.4.C	C. Manufacturer Seismic Qualification Certification	238223 - 1.4.D	D. Operation and Maintenance Data					238223 -1.4.A A. Product Data	238223 - 1.4.B B. Shop Drawings	238223 - 1.4.C C. Manufacturer Seismic Qualification Certification	238223 - 1.4.D D. Operation and Maintenance Data
238239	Cabinet Unit Heaters	5/15/2024	238239 - 1.3.A	A. Product Data:	238239 - 1.3.B	B. Shop Drawings	238239 - 1.3.C	C. Samples for Initial Selection	238239 - 1.3.D	D. Field quality-control test reports	238239 - 1.3.E	E. Operation and Maintenance Data					238239 - 1.3.A A. Product Data:	238239 - 1.3.B B. Shop Drawings	238239 - 1.3.C C. Samples for Initial Selection	238239 - 1.3.D D. Field quality-control test reports	238239 - 1.3.E E. Operation and Maintenance Data
23 2113.33	Ground-Loop Heat-Pump Piping	5/15/2024	23 2113.33 - 1.4.A	A. Product Data	23 2113.33 -1.4.B	B. Field quality-control test reports					23 2113.33 - 1.4.A A. Product Data	23 2113.33 -1.4.B B. Field quality-control test reports
78100	Applied Fireproofing	6/1/2024	78100 - 1.4.A.1	1. Product Data	78100 - 1.4.A.2	2. Performance Certification	78100 - 1.4.A.3	3. Testing Agency qualifications					78100 - 1.4.A.1 1. Product Data	78100 - 1.4.A.2 2. Performance Certification	78100 - 1.4.A.3 3. Testing Agency qualifications
78123	Intumescent Fire Protection	6/1/2024	78123 - 1.5.A.1	1. Manufacturer's Data					78123 - 1.5.A.1 1. Manufacturer's Data
78413	Penetration Firestopping	6/1/2024	78413 - 1.6.A.1	1. Product Data	78413 - 1.6.A.2	2. Shop Drawings	78613 - 1.6.A.3	3. Firestop System Schedule	78613 - 1.6.A.4	4. Product Test Reports	78613 - 1.6.A.5	5. Qualification Data					78413 - 1.6.A.1 1. Product Data	78413 - 1.6.A.2 2. Shop Drawings	78613 - 1.6.A.3 3. Firestop System Schedule	78613 - 1.6.A.4 4. Product Test Reports	78613 - 1.6.A.5 5. Qualification Data
78446	Fire-Resistive Joint Systems	6/1/2024	78446 - 1.5.A.1	1. Product Data:	78446 - 1.5.A.2	2. Color selection charts where applicable	78446 - 1.5.A.3	3. Shop Drawings:	78446 - 1.5.A.4	4. Product Test Reports	78446 - 1.5.A.5	5. Qualification Data					78446 - 1.5.A.1 1. Product Data:	78446 - 1.5.A.2 2. Color selection charts where applicable	78446 - 1.5.A.3 3. Shop Drawings:	78446 - 1.5.A.4 4. Product Test Reports	78446 - 1.5.A.5 5. Qualification Data
79200	Joint Sealants	6/1/2024	79200 - 1.6.A.1	1. Submit manufacturer's product data for each sealant/product	79200 - 1.6.A.2	2. Compatibility and Adhesion Test Reports	79200 - 1.6.A.3	3. Certificates	79200 - 1.6.A.4	4. Samples for Initial Selection	79200 - 1.6.A.5	5. Qualification Data					79200 - 1.6.A.1 1. Submit manufacturer's product data for each sealant/product	79200 - 1.6.A.2 2. Compatibility and Adhesion Test Reports	79200 - 1.6.A.3 3. Certificates	79200 - 1.6.A.4 4. Samples for Initial Selection	79200 - 1.6.A.5 5. Qualification Data
96623	Epoxy Terrazzo	6/1/2024	96623 - 1.4.A.1	1. Shop drawings and product data	96623 - 1.4.A.2	2. Samples	96623 - 1.4.B.1	1. O&M Data					96623 - 1.4.A.1 1. Shop drawings and product data	96623 - 1.4.A.2 2. Samples	96623 - 1.4.B.1 1. O&M Data
323119	Fences and Gates	6/1/2024	323119 - 1.4.A	A. Manufacturer					323119 - 1.4.A A. Manufacturer
12 3553.19	Wood Laboratory Casework	6/1/2024	12 3553.19 -1.4.A.1	1. Manufacturer's data	12 3553.19 - 1.4.A.2	2. Samples	12 3553.19 - 1.4.A.3	3. Shop Drawings	12 3553.19 - 1.4.A.4	4. Roughing-in Drawings	12 3553.19 - 1.4.A.5	5. Certificates	12 3553.19 - 1.4.B.1	1. Operating and Maintenance Data	12 3553.19 - 1.4.B.2	2. Operations Equipment					12 3553.19 -1.4.A.1 1. Manufacturer's data	12 3553.19 - 1.4.A.2 2. Samples	12 3553.19 - 1.4.A.3 3. Shop Drawings	12 3553.19 - 1.4.A.4 4. Roughing-in Drawings	12 3553.19 - 1.4.A.5 5. Certificates	12 3553.19 - 1.4.B.1 1. Operating and Maintenance Data	12 3553.19 - 1.4.B.2 2. Operations Equipment
62000	Finish Carpentry	6/15/2024	62000 - 1.4.1	1. Submit shop drawings and product data	62000 - 1.4.2	2. Submit the following samples: a. Plastic laminates					62000 - 1.4.1 1. Submit shop drawings and product data	62000 - 1.4.2 2. Submit the following samples: a. Plastic laminates
99100	Paints and Coatings	7/1/2024	99100 - 1.5.A.1	1. Product Data	99100 - 1.5.A.2	2. Schedule	99100 - 1.5.A.3	3. Documentation that the manufacturer has reviewed and approved	99100 - 1.5.A.4	4. Samples for Initial Selection	99100 - 1.5.A.5	5. Samples for Verification	99100 - 1.5.A.6	6. Qualification Data	99100 - 1.5.B.1	1. Provide one drawdown of each paint finish and one wood sample for each stained	99100 - 1.5.B.2	2. Provide Maintenance Stock materials					99100 - 1.5.A.1 1. Product Data	99100 - 1.5.A.2 2. Schedule	99100 - 1.5.A.3 3. Documentation that the manufacturer has reviewed and approved	99100 - 1.5.A.4 4. Samples for Initial Selection	99100 - 1.5.A.5 5. Samples for Verification	99100 - 1.5.A.6 6. Qualification Data	99100 - 1.5.B.1 1. Provide one drawdown of each paint finish and one wood sample for each stained	99100 - 1.5.B.2 2. Provide Maintenance Stock materials
126600	Telescoping Stands	7/15/2024	126600 - 1.3.A.1	1. Product Data	126600 - 1.3.A.2	2. Shop Drawings	126600 - 1.3.A.3	3. Samples for Initial Selection	126600 - 1.3.A.4	4. Samples for Verification	126600 - 1.3.A.5	5. Qualification Data	126600 - 1.3.B.1	1. Operation and Maintenance Data					126600 - 1.3.A.1 1. Product Data	126600 - 1.3.A.2 2. Shop Drawings	126600 - 1.3.A.3 3. Samples for Initial Selection	126600 - 1.3.A.4 4. Samples for Verification	126600 - 1.3.A.5 5. Qualification Data	126600 - 1.3.B.1 1. Operation and Maintenance Data
81400	Wood Doors	8/1/2024	81400 - 1.4.A.1	1. Product Data	81400 - 1.4.A.2	2. Shop Drawings					81400 - 1.4.A.1 1. Product Data	81400 - 1.4.A.2 2. Shop Drawings
83100	Access Panels and Frames	8/1/2024	83100 - 1.3.A.1	1. Manufacturer's Data	83100 - 1.3.A.2	2. Shop Drawings	83100 - 1.3.B.1	1. Keys					83100 - 1.3.A.1 1. Manufacturer's Data	83100 - 1.3.A.2 2. Shop Drawings	83100 - 1.3.B.1 1. Keys
83300	Coiling Doors and Grilles	8/1/2024	83300 - 1.3.A	A. Product Data	83300 - 1.3.B	B. Shop Drawings	83300 - 1.3.C	C. Samples	83300 - 1.3.D	D. Qualification statement	83300 - 1.3.E	E. Operation and Maintenance data					83300 - 1.3.A A. Product Data	83300 - 1.3.B B. Shop Drawings	83300 - 1.3.C C. Samples	83300 - 1.3.D D. Qualification statement	83300 - 1.3.E E. Operation and Maintenance data
84113	Aluminum Entrances & Storefronts	8/1/2024	84113 - 1.4.A.1	1. Product Data	84113 - 1.4.A.2	2. Shop Drawings	84113 - 1.4.A.3	3. Samples for Initial Selection	84113 - 1.4.A.4	4. Samples for Verification	84113 - 1.4.A.5	5. Cutaway sample	84113 - 1.4.A.6	6. Installer Certificates					84113 - 1.4.A.1 1. Product Data	84113 - 1.4.A.2 2. Shop Drawings	84113 - 1.4.A.3 3. Samples for Initial Selection	84113 - 1.4.A.4 4. Samples for Verification	84113 - 1.4.A.5 5. Cutaway sample	84113 - 1.4.A.6 6. Installer Certificates
84500	Translucent Wall Assemblies	8/1/2024	84500 - 1.4.A.1	1. Submit product data and installation instructions	84500 - 1.4.A.2	2. Shop Drawings	84500 - 1.4.A.3	3. Submit substantiating engineering data, test results					84500 - 1.4.A.1 1. Submit product data and installation instructions	84500 - 1.4.A.2 2. Shop Drawings	84500 - 1.4.A.3 3. Submit substantiating engineering data, test results
85113	Aluminum Windows	8/1/2024	85113 - 1.5.A.1	1. Product Data	85113 - 1.5.A.2	2. Shop Drawings	85113 - 1.5.A.3	3. Samples	85113 - 1.5.A.4	4. Certifications	85113 - 1.5.A.5	5. Warranty					85113 - 1.5.A.1 1. Product Data	85113 - 1.5.A.2 2. Shop Drawings	85113 - 1.5.A.3 3. Samples	85113 - 1.5.A.4 4. Certifications	85113 - 1.5.A.5 5. Warranty
87100	Hardware	8/1/2024	87100 - 1.6.A.1	1. Submit supplier qualifications	87110 - 1.6.A.2	2. Product Data	87110 - 1.6.A.3	3. Hardware Schedule	87110 - 1.6.A.4	4. Samples and Templates	87110 - 1.6.A.5	5. Keying Schedule					87100 - 1.6.A.1 1. Submit supplier qualifications	87110 - 1.6.A.2 2. Product Data	87110 - 1.6.A.3 3. Hardware Schedule	87110 - 1.6.A.4 4. Samples and Templates	87110 - 1.6.A.5 5. Keying Schedule
88000	Glazing	8/1/2024	88000 - 1.6.A.1	1. Manufacturer's Data - Glazing	88000 - 1.6.A.2	2. Manufacturer's Data - Glazing Materials	88000 - 1.6.A.3	3. Samples for verification	88000 - 1.6.A.4	4. Compatibility test report from manufacturer of insulating glass edge sealant	88000 - 1.6.A.5	5. Product test reports for each type of glazing sealant and gasket	88000 - 1.6.B.1	1. Maintenance data for glass and other glazing materials					88000 - 1.6.A.1 1. Manufacturer's Data - Glazing	88000 - 1.6.A.2 2. Manufacturer's Data - Glazing Materials	88000 - 1.6.A.3 3. Samples for verification	88000 - 1.6.A.4 4. Compatibility test report from manufacturer of insulating glass edge sealant	88000 - 1.6.A.5 5. Product test reports for each type of glazing sealant and gasket	88000 - 1.6.B.1 1. Maintenance data for glass and other glazing materials
93000	Tile	9/1/2024	93000 - 1.4.A.1	1. Submit shop drawings	93000 - 1.4.A.2	2. Submit product data	93000 - 1.4.A.3	3. Samples	93000 - 1.4.B.1	1. Maintenance Instructions	93000 - 1.4.B .2	2. Provide Maintenance Stock materials					93000 - 1.4.A.1 1. Submit shop drawings	93000 - 1.4.A.2 2. Submit product data	93000 - 1.4.A.3 3. Samples	93000 - 1.4.B.1 1. Maintenance Instructions	93000 - 1.4.B .2 2. Provide Maintenance Stock materials
95100	Acoustical Ceilings	9/15/2024	95100 - 1.6.A.1	1. Submit product data	95100 - 1.6.A.2	2. Submit manufacturer's installation instructions	95100 - 1.6.A.3	3. Samples	95100 - 1.6.B.1	1. Provide manufacturer's cleaning information	95100 - 1.6.B.2	2. Provide Maintenance Stock materials					95100 - 1.6.A.1 1. Submit product data	95100 - 1.6.A.2 2. Submit manufacturer's installation instructions	95100 - 1.6.A.3 3. Samples	95100 - 1.6.B.1 1. Provide manufacturer's cleaning information	95100 - 1.6.B.2 2. Provide Maintenance Stock materials
274116.62	Cafetorium Sound Reinforcement Systems	9/15/2024	274116.62 - 1.4.A	A. shop drawings and schedules	274116.62 - 1.4.B	B. system book					274116.62 - 1.4.A A. shop drawings and schedules	274116.62 - 1.4.B B. system book
274116.63	Gymnasium Sound Reinforcement Systems	9/15/2024	274116 .63 - 1.4.A	A. shop drawings and schedules	274116 .63 - 1.4.B	B. system book					274116 .63 - 1.4.A A. shop drawings and schedules	274116 .63 - 1.4.B B. system book
96500	Resilient Flooring	10/1/2024	96500 - 1.4.A.1	1. Product Data	96500 - 1.4.A.2	2. Initial Samples	96500 - 1.4.A.3	3. Installation Instructions	96500 - 1.4.B.1	1. Maintenance Instructions	96500 - 1.4.B.2	2. Provide Maintenance Stock materials					96500 - 1.4.A.1 1. Product Data	96500 - 1.4.A.2 2. Initial Samples	96500 - 1.4.A.3 3. Installation Instructions	96500 - 1.4.B.1 1. Maintenance Instructions	96500 - 1.4.B.2 2. Provide Maintenance Stock materials
96466	Wood Athletic Flooring	10/15/2024	96466 - 1.3.A.1	1. Product Data:	96466 - 1.3.A.2	2. Shop Drawings	96466 - 1.3.A.3	3. Qualification Data	96466 - 1.3.A.4	4. Samples for Initial Selection	96466 - 1.3.A.5	5. Samples for Verification	96466 - 1.3.B.1	1. Maintenance Instructions					96466 - 1.3.A.1 1. Product Data:	96466 - 1.3.A.2 2. Shop Drawings	96466 - 1.3.A.3 3. Qualification Data	96466 - 1.3.A.4 4. Samples for Initial Selection	96466 - 1.3.A.5 5. Samples for Verification	96466 - 1.3.B.1 1. Maintenance Instructions
96800	Carpet	11/1/2024	96800 - 1.4.A.1	1. Submit shop drawings, product data, samples, and installation instructions	96800 - 1.4.A.2	2. Submit manufacturer's warranty for materials specified	96800 - 1.4.A.3	3. Submit actual tile in size as specified	96800 - 1.4.B.1	1. Submit operational and maintenance data	96800 - 1.4.B.2	2. Warranty Certificates	96800 - 1.4.B.3	3. Provide "Excess Materials"	96800 - 1.4.B.4	4. Provide Maintenance Stock materials					96800 - 1.4.A.1 1. Submit shop drawings, product data, samples, and installation instructions	96800 - 1.4.A.2 2. Submit manufacturer's warranty for materials specified	96800 - 1.4.A.3 3. Submit actual tile in size as specified	96800 - 1.4.B.1 1. Submit operational and maintenance data	96800 - 1.4.B.2 2. Warranty Certificates	96800 - 1.4.B.3 3. Provide "Excess Materials"	96800 - 1.4.B.4 4. Provide Maintenance Stock materials
102113.19	Plastic Toilet Compartments	11/1/2024	102113.19 - 1.4.A.1	1. Product Data	102113.19 - 1.4.A.2	2. Shop Drawings	102113.19 - 1.4.A.3	3. Samples for Initial Selection	102113.19 - 1.4.A.4	4. Panel Color Verification Samples	102113.19 - 1.4.A.5	5. Manufacturer's Instructions	102113.19 - 1.4.B	1. O&M Data					102113.19 - 1.4.A.1 1. Product Data	102113.19 - 1.4.A.2 2. Shop Drawings	102113.19 - 1.4.A.3 3. Samples for Initial Selection	102113.19 - 1.4.A.4 4. Panel Color Verification Samples	102113.19 - 1.4.A.5 5. Manufacturer's Instructions	102113.19 - 1.4.B 1. O&M Data
122000	Window Treatments	11/1/2024	122000 - 1.4.A.1.a	a. Product data	122000 - 1.4.A.1.b	b. Manufacturer's installation instructions	122000 - 1.4.A.1.c	c. Samples					122000 - 1.4.A.1.a a. Product data	122000 - 1.4.A.1.b b. Manufacturer's installation instructions	122000 - 1.4.A.1.c c. Samples
-291919	Visual Display Surfaces	11/1/2024	10 1100 - 1.4.A.1	1. Shop drawings	10 1100 - 1.4.A.2	2. Product data	10 1100 - 1.4.A.2	3. Samples for initial selection	10 1100 - 1.4.B.1	1. O&M Data	10 1100 - 1.4.B.2	2. Materials					10 1100 - 1.4.A.1 1. Shop drawings	10 1100 - 1.4.A.2 2. Product data	10 1100 - 1.4.A.2 3. Samples for initial selection	10 1100 - 1.4.B.1 1. O&M Data	10 1100 - 1.4.B.2 2. Materials
-255394	Display Cases	11/1/2024	10 1200 - 1.4.A	Product Data	10 1200 - 1.4.B	Shop Drawings	10 1200 - 1.4.C	Product Test Reports	10 1200 - 1.4.D	Maintenance Data					10 1200 - 1.4.A Product Data	10 1200 - 1.4.B Shop Drawings	10 1200 - 1.4.C Product Test Reports	10 1200 - 1.4.D Maintenance Data
-182346	Signage	11/1/2024	10 1400 - 1.3.A.1	1. Shop Drawings	10 1400 - 13.A.2	2. Product Data	10 1400 - 13.A.3	3. Samples: Submit paint samples to allow color comparison	10 1400 - 13.A.4	4. Samples: Submit frame samples	10 1400 - 13.A.5	5. Fabrication will not begin until all submittals have been approved					10 1400 - 1.3.A.1 1. Shop Drawings	10 1400 - 13.A.2 2. Product Data	10 1400 - 13.A.3 3. Samples: Submit paint samples to allow color comparison	10 1400 - 13.A.4 4. Samples: Submit frame samples	10 1400 - 13.A.5 5. Fabrication will not begin until all submittals have been approved
275	Hospital Cubicles	11/1/2024	10 1900 - 1.3.B	Submit manufacturer's data, color charts, detail drawings and installation instructions	10 1900 - 1.3.C	Samples					10 1900 - 1.3.B Submit manufacturer's data, color charts, detail drawings and installation instructions	10 1900 - 1.3.C Samples
114596	Wire Mesh Partitions	11/1/2024	10 2213 - 1.5.A.1	1. Manufacturer's Data	10 2213 - 1.5.A.2	2. Shop Drawings					10 2213 - 1.5.A.1 1. Manufacturer's Data	10 2213 - 1.5.A.2 2. Shop Drawings
119344	Operable Partitions	11/1/2024	10 2226 - 1.3.A.1	1. Reference Submittals	10 2226 - 1.3.A.2	2. Product Data	10 2226 - 1.3.A.3	3. Samples	10 2226 - 1.3.A.4	4. Shop Drawings	10 2226 - 1.3.A.5	5. Warranty	10 2226 - 1.3.B.1	1. O&M Data	10 2226 - 1.3.B.2	2. Operations Equipment					10 2226 - 1.3.A.1 1. Reference Submittals	10 2226 - 1.3.A.2 2. Product Data	10 2226 - 1.3.A.3 3. Samples	10 2226 - 1.3.A.4 4. Shop Drawings	10 2226 - 1.3.A.5 5. Warranty	10 2226 - 1.3.B.1 1. O&M Data	10 2226 - 1.3.B.2 2. Operations Equipment
98400	Acoustic Wall Panels	11/15/2024	98400 - 1.6.A.1	1. Product Data	98400 - 1.6.A.2	2. Shop Drawings	98400 - 1.6.A.3	3. Samples	98400 - 1.6.B.1	1. Maintenance Instructions					98400 - 1.6.A.1 1. Product Data	98400 - 1.6.A.2 2. Shop Drawings	98400 - 1.6.A.3 3. Samples	98400 - 1.6.B.1 1. Maintenance Instructions
102800	Toilet, Bath, and Laundry Accessories	11/15/2024	102800 - 1.3.A.1	1. Manufacturer's data	102800 - 1.3.A.2	2. Setting drawings	102800 - 1.3.B.1	1. O&M Data	102800 - 1.3.B.2	2. Operations Equipment					102800 - 1.3.A.1 1. Manufacturer's data	102800 - 1.3.A.2 2. Setting drawings	102800 - 1.3.B.1 1. O&M Data	102800 - 1.3.B.2 2. Operations Equipment
104400	Fire Protection Specialties	11/15/2024	104400 - 1.3.A.1	1. Submit Manufacturer's technical data and installation instructions					104400 - 1.3.A.1 1. Submit Manufacturer's technical data and installation instructions
105100	Lockers	11/15/2024	105100 - 1.3.A.1	1. Product Data	105100 - 1.3.A.2	2. Shop Drawings	105100 - 1.3.A.3	3. Samples	105100 - 1.3.A.4	4. Qualification Data	105100 - 1.3.A.5	5. Warranty	105100 - 1.3.B.1	1. Maintenance Data					105100 - 1.3.A.1 1. Product Data	105100 - 1.3.A.2 2. Shop Drawings	105100 - 1.3.A.3 3. Samples	105100 - 1.3.A.4 4. Qualification Data	105100 - 1.3.A.5 5. Warranty	105100 - 1.3.B.1 1. Maintenance Data
114520	Residential Appliances	12/1/2024	114520 - 1.4.B	B. Provide product data on range hoods	114520 - 1.4.C	C. Submit manufacturer's installation instruction					114520 - 1.4.B B. Provide product data on range hoods	114520 - 1.4.C C. Submit manufacturer's installation instruction
-474509	Theatre and Stage Equipment	12/1/2024	11 0600 - 1.7.A	Submit six sets of shop drawings	11 0600 - 1.7.B	Submit one color card sample of each type of fabric	11 0600 - 1.7.C	Samples of equipment components required by the architect or owner					11 0600 - 1.7.A Submit six sets of shop drawings	11 0600 - 1.7.B Submit one color card sample of each type of fabric	11 0600 - 1.7.C Samples of equipment components required by the architect or owner
767316	Food Service Equipment	12/1/2024	11 4000 - 1.4	FIRST YEAR GUARANTEE	11 4000 - 1.6	ROUGH-IN DRAWINGS	11 4000 -1.7	OPERATION AND MAINTENANCE DATA					11 4000 - 1.4 FIRST YEAR GUARANTEE	11 4000 - 1.6 ROUGH-IN DRAWINGS	11 4000 -1.7 OPERATION AND MAINTENANCE DATA
1210355	Projection Screens	12/1/2024	11 5213 - 1.4.A.1	1. Product Data	11 5213 - 1.4.A.2	2. Shop Drawings	11 5213 - 1.4.B.1	1. O&M Data	11 5213 - 1.4.B.2	2. Operations Equipment					11 5213 - 1.4.A.1 1. Product Data	11 5213 - 1.4.A.2 2. Shop Drawings	11 5213 - 1.4.B.1 1. O&M Data	11 5213 - 1.4.B.2 2. Operations Equipment
1246879	Laboratory Fume Hood	12/1/2024	11 5313 - 1.3.A.1	1. Shop Drawings	11 5313 - 1.3.A.2	2. Product Data	11 5313 - 1.3.A.3	3. Samples	11 5313 - 1.3.A.4	4. Certificates	11 5313 - 1.3.B.1	1. Operating and Maintenance Data	11 5313 - 1.3.B.2	2. Operating instructions to be inscribed on instruction plate	11 5313 - 1.3.B.3	3. Written instructions in booklet form	11 5313 - 1.3.B.4	4. Professional quality video	11 5313 - 1.3.B.5	5. Certificates			11 5313 - 1.3.A.1 1. Shop Drawings	11 5313 - 1.3.A.2 2. Product Data	11 5313 - 1.3.A.3 3. Samples	11 5313 - 1.3.A.4 4. Certificates	11 5313 - 1.3.B.1 1. Operating and Maintenance Data	11 5313 - 1.3.B.2 2. Operating instructions to be inscribed on instruction plate	11 5313 - 1.3.B.3 3. Written instructions in booklet form	11 5313 - 1.3.B.4 4. Professional quality video	11 5313 - 1.3.B.5 5. Certificates
1716946	Athletic Equipment	12/1/2024	11 6600 - 1.4.A.1	1. Product Data	11 6600 - 1.4.A.2	2. Shop Drawings	11 6600 - 1.4.A.3	3. Coordination Drawings	11 6600 - 1.4.A.4	4. Samples for Verification	11 6600 - 1.4.A.5	5. Manufacturer Certificates	11 6600 - 1.4.A.6	6. Warranty Certificates	11 6600 - 1.4.B.1	1. O&M Data	11 6600 - 1.4.B.2	2. Operations Equipment					11 6600 - 1.4.A.1 1. Product Data	11 6600 - 1.4.A.2 2. Shop Drawings	11 6600 - 1.4.A.3 3. Coordination Drawings	11 6600 - 1.4.A.4 4. Samples for Verification	11 6600 - 1.4.A.5 5. Manufacturer Certificates	11 6600 - 1.4.A.6 6. Warranty Certificates	11 6600 - 1.4.B.1 1. O&M Data	11 6600 - 1.4.B.2 2. Operations Equipment
2118409	Closeout Procedures	2/5/2025	01 7700 - 1.6	PROJECT RECORD DOCUMENTS	01 7700 - 1.7	OPERATION AND MAINTENANCE DATA	01 7700 - 1.8	WARRANTIES	01 7700 - 1.9	SPARE PARTS, KEYS, AND MAINTENANCE MATERIALS					01 7700 - 1.6 PROJECT RECORD DOCUMENTS	01 7700 - 1.7 OPERATION AND MAINTENANCE DATA	01 7700 - 1.8 WARRANTIES	01 7700 - 1.9 SPARE PARTS, KEYS, AND MAINTENANCE MATERIALS

## Data
Specification Section- Description- Subcontractor:- Submit By:- DATE:- Attachments Link:- 0- 0- Log 9- Log 10- Log 11- Log 12					Specification Section	Description	Subcontractor:	Submit By:	DATE:	Attachments Link:	0	0	Log 9	Log 10	Log 11	Log 12	Date Returned:	Remaks:	Update 3
33000- 33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , , - Company- 45298- 45342- https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link- - - - - -	Specification Section	Description	Subcontractor:	Submit By:	DATE:	Attachments Link:			Log 9	Log 10	Log 11	Log 12	Date Returned:	Remaks:	Update 3		Refresh	33000	33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , ,	Company	45298	45342	https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link					0	0	0			LETTER OF TRANSMITTAL					Company					JOB:	Example Project					Business Street		DATE:	45342					Business City, Business State Business Postal Code					PHONE:	Business Phone	RE:	Specification Section		33000					FAX:	Business Fax		Concrete					TO:					Company					Business Street					Business City, Business State Business Postal Code					ATTN:	First Name Middle Name Last Name					Email:	E-mail Address					We are sending:					QTY	DATED	DESCRIPTION					33000 -1.4.1 1. Manufacturer's Data, 33000 - 1.4.2 2. Shop Drawings, 33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials, , , , , , ,					1		33000 -1.4.1 1. Manufacturer's Data					1		33000 - 1.4.2 2. Shop Drawings					1		33000 - 1.4.3 3. Contractor's Laboratory Test Reports on Concrete Mix Design and Materials					These are transmitted for your review.					PLEASE NOTE THE FOLLOWING:					kjvlk/ldfkj					SIGNED:___					Subcontractor:					Company			Submit By:	45298					CC:			Date Returned:					Attachments Link:		https://drive.google.com/file/d/1bNx2JSVmj-XvIkJ4SMi37Z7Jjbg4j8Bv/view?usp=drive_link					Remaks:

## NewContact1
First Name
Middle Name
Last Name			Save Contact		To import contacts: Export your selected Gmail™ contacts to an Outlook™ CSV file. Open it and 'Select all' (Ctrl+A) then press (Ctrl+C) to copy. Paste them (Ctl+V) in the green shaded (First Name) cell (C1) on the contacts sheet.
Company
Business Street
Business City
Business State
Business Postal Code
E-mail Address
Business Phone
Business Fax
Home Street
Home City
Home State
Home Postal Code
Other Street
Other City
Other State
Other Postal Code
Title
Home Phone
Mobile Phone

## contacts1
Company	First Name Middle Name Last Name	First Name	Middle Name	Last Name	Title					E-mail Address				Home Phone		Mobile Phone				Home Street				Home City	Home State	Home Postal Code					Business Phone		Business Fax		Company					Business Street				Business City	Business State	Business Postal Code					Other Street				Other City	Other State	Other Postal Code
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0